## Roadmap
Finance Tracker — Feature Roadmap
Phases and features. Edit Status as work progresses — Summary sheet updates automatically.
Phase | Feature | Description | Owner Role | Status | Priority | Notes
v1 | Single-user login | Session-based auth, one seeded account. No registration flow. | Dev | Done | Must | Built; not yet run/verified locally
v1 | Categories (fixed, editable list) | Seeded income/expense categories; add or delete from the Categories page. | Dev | Done | Must | Built; not yet run/verified locally
v1 | Manual transaction entry | Log a transaction: amount, date, category, note, income or expense. | Dev | Done | Must | Built; not yet run/verified locally
v1 | Edit / delete transaction | Correct mistakes without re-entering everything. | Dev | Done | Must | Built; not yet run/verified locally
v1 | Transactions list, filtered by month | Table view of all transactions for the selected month. | Dev | Done | Must | Built; not yet run/verified locally
v1 | Dashboard: income vs. expense + category breakdown | Totals for the selected month and a per-category expense breakdown. | Dev | Done | Must | Built; not yet run/verified locally
v1 | Deploy v1 somewhere reachable from phone | Ship it — even a cheap VPS or free host counts. | PM | Not Started | Must | Blocks 'used daily for 14 days' success criterion
v1 | Use daily for 14 days | The actual test of whether v1 succeeded — not a feature, a milestone. | PM | Not Started | Must | See QA Checklist sheet + Success Criteria below
v2 | Budgets vs. actuals | Set a monthly budget per category, compare against real spending. | BA/Dev | Parked | Should | Do not start until v1 used for 2+ weeks
v2 | Recurring transactions / bill reminders | Auto-log or remind about recurring bills. | BA/Dev | Parked | Should | Do not start until v1 used for 2+ weeks
v2 | CSV import | Import transactions exported from bank/e-wallet statements. | BA/Dev | Parked | Could | Cuts manual entry effort once v1 habit is proven
v3 | Reports / export (PDF, Excel) | Export monthly or yearly summaries. | BA/Dev | Parked | Could | Only valuable once there's enough real data
v3 | Net worth / account balance tracking | Track balances across accounts toward a savings goal. | BA/Dev | Parked | Could | Adds a second core concept beyond transactions
v3 | Multi-currency | Support more than one currency. | BA/Dev | Parked | Won't (for now) | Only if actually needed
v4 | Mobile app (Expo / React Native) | Native mobile app instead of the mobile-web dashboard. | BA/Dev | Parked | Won't (for now) | This exact scope sank the previous attempt — revisit deliberately
v4 | Bank / e-wallet API sync (GCash, banks, etc.) | Automatic transaction sync instead of manual entry. | BA/Dev | Parked | Won't (for now) | Highest effort + highest risk item — last, if ever
v4 | Multi-user / household sharing | Shared budgets/expenses with another person. | BA/Dev | Parked | Won't (for now) | Out of scope for a personal tracker
Legend
Status and Priority cells are dropdowns — click a cell to change it.

## Summary
Finance Tracker — Progress Summary
Counts pull live from the Roadmap sheet — edit Status there, this updates automatically.
Status | Count
Done | 6
In Progress | 0
Not Started | 2
Parked | 9
Total features | 17
Phase | Total | Done | Not Started / Parked
v1 | 8 | 6 | 2
v2 | 3 | 0 | 3
v3 | 3 | 0 | 3
v4 | 3 | 0 | 3

## QA Checklist (v1)
Finance Tracker — v1 QA Checklist
Run through before calling v1 (or any milestone) "done". Mark Checked = Yes as you verify each one.
# | Check | Checked?
1 | Can log in with the seeded account, and logging out actually blocks access | No
2 | Can add a transaction (both income and expense) and see it reflected in the dashboard totals immediately | No
3 | Can edit and delete a transaction | No
4 | Dashboard totals are correct for a month with mixed income/expense entries | No
5 | Category breakdown on the dashboard matches the transactions list for the same month | No
6 | Filtering by month works on both the Dashboard and Transactions pages | No
7 | Can add and delete a category (delete is blocked if it has transactions) | No
8 | Works on a mobile browser (the likely daily-use context) | No
9 | A fresh composer install && npm install && migrate --seed on a clean checkout works without manual fixes | No
Passed |  | 0 / 9